2016 Venice Neighborhood Council Election Timeline

| Rel to Election Day | Date | Julian Date | Elec Comm | Outreach Comm | Activity |
| --- | --- | --- | --- | --- | --- |
| now |  |  | x | x | Joint Elections Committee/Outreach Committee meeting to determine roles and responsibilities of each |
| now |  |  |  | x | Create "Interested in Running for Board Seat" sign-up sheets. These sheets should be available at every VNC event until candidate filing begins. |
| now | for dist at 17 Nov VNC Board mtg |  |  | x | Create recruitment flyers, wording to be validated by elec comm |
| now |  |  | x |  | Create timeline merging empowerla events and VNC election activities, dates to be validated by outreach comm |
| now |  |  | x | x | Investigate newsletter creation and distribution costs |
| now |  |  |  | x | Investigate cost of outreach to apts/condos within boundaries - peninsula and southern portion of Oxford Triangle especially have Marina Del Rey addresses and may not know they are stakeholders in VNC. |
| now |  |  | x |  | Determine election events, approximate dates and approximate locations desired; Will there be a newsletter? Will newsletter photo be the same as that submitted to empowerla? Appoint newsletter liaison. |
| now |  |  | x |  | estimate costs to be covered by Elections Comm |
| now |  |  | x |  | Get budget for Elec Comm responsibilities -- done |
|  |  |  |  |  | If an election newsletter is wanted and feasible: Select and secure publisher Select and secure distributor If photo other than what was submitted to emowerla will be allowed, add photo/stmt deadline to the election timeline (at least 3 weeks prior to the newsletter distribution date) |
|  |  |  |  | x | Plan the recruitment events - what will attract. Event attendance should target by age (Senior citizens, middle age, young adults, youth 16 & up), consider ethnic groups, and be spread geographically within the boundaries of VNC Themes Publicity Decoration handouts |
|  |  |  | x |  | Plan the programs for the recruitment events Board members to attend Photo-op City officials |
|  |  |  |  | x | Secure locations for recruitment events |
|  |  |  |  | x | Secure refreshments for recruitment events |
|  |  |  | x |  | Secure additional resources for recruitment events Photographer Board Officers Council Office Mayor's Office Testamonials |
|  |  |  | x |  | Secure location for Candidate Orientation |
|  |  |  | x |  | Secure refreshments for Candidate Orientation |
|  |  |  |  |  | Add VNC events and details to timeline on venicenc.org |
|  |  |  |  |  | Send list of VNC events to empowerla for their web site |
| -90 | 7 Mar | 67 |  |  | Candidate filing opens |
|  |  |  |  | x | Have candidate recruitment flyers available at every possible event, especially non-VNC events |
|  |  |  |  | x | Speak at meeting of other orgs, such as Chamber of Commerce, Recruit candidates by speaking at various organizations' meetings |
|  |  |  | x | x | Recruitment event 1 - mixer |
|  |  |  | x |  | Begin informative bulletins to prospective candidates. Continue bulletins to prospective and actual candidates until electon. They need lots of reminders about deadlines. |
|  |  |  |  |  | Plan Candidate Orientation program Amount of time VNC responsibilities will require Ethics training is required of all Board officers Campaigning includes social media Effective places to campaign Effective ways to campaign |
|  |  |  |  |  | Develop and print Candidate Orientation handout materials. Campaign starter set VOTE cards with candidate list VOTE flyers Campaign Guidelines |
|  |  |  | x | x | Recruitment event 2 |
|  |  |  |  |  | Preliminary plan for Board Orientation Tutorials By-laws Whatever is normally covered Council Office City Atty Office |
|  |  |  | x | x | Recruitment event 3 |
|  |  |  |  |  | Immediately after recruitment event 3 |
| -60 | 6 Apr | 97 |  |  | Candidate filing closes |
|  |  |  |  |  | Candidate campaigning begins |
|  |  |  |  |  | Election Day volunteer recruitment begins |
| -57 | 9 Apr | 100 |  |  | empowerla deadline to submit candidate photos and statements for their web site |
| -57 | 9 Apr | 100 |  |  | deadline for submitting candidate's verifying documents |
| -57? |  |  |  |  | Empowerla releases the final verified list of candidates |
| -55 | 11 Apr | 102 | x |  | Candidate orientation |
| ?+3 |  |  |  |  | Deadline for challenging any candidate's eligibility |
|  |  |  |  | x | Voter awareness begins |
|  |  |  |  |  | Detailed plan for Board orientation |
| -45 | 21 Apr | 112 |  |  | Final day a candidate can withdraw and have name removed from the ballot |
| -45 | 21 Apr | 112 |  |  | City Clerk will release the final verified candidate list |
| -45 | 21 Apr | 112 |  |  | No later than this date, empowerla will give candidate contact information to his/her neighborhood council |
| -45 | 21 Apr | 112 |  |  | Voter drive begins |
| -45 | 21 Apr | 112 |  |  | Begin development of exit poll or survey |
| -45 | 21 Apr | 112 |  |  | Begin recruitment of voting process volunteers |
| -45 | 21 Apr | 112 |  |  | Begin recruitment of counting volunteers |
| -30 | 6 May | 127 |  |  | Deadline for empowerla to put election location on its web site. If changed, the change will be on the web site within 24 hours. |
|  |  |  |  |  | Complete arrangements for new Board's orientation Requirements Guest speakers Tutorials Absentees |
|  |  |  |  |  | Plan Forum(s) Room layout handouts logistics for questions from audience create samples to make sure there are adequate questions Question guidelines Impartial Not embarrassing Confirm capability Occupation vision of Venice Neighborhood Council |
|  |  |  |  |  | Monitor newsletter preparation |
|  |  |  |  |  | Print all Forum Handouts |
| -21 | 15 May | 136 |  |  | Deadline for newsletter photos and statements |
|  |  |  |  |  | Print handouts, committee signup sheets, etc for outreach table that will be at poll exit |
| -10 | 26 May | 147 |  |  | Distribute newsletters |
| -3 | 2 Jun | 154 |  |  | Forum A |
| -2 | 3 Jun | 155 |  |  | Forum B |
| 0 | 5 Jun | 157 | x |  | Election day Assist with election set-up Assist with election Assist at outreach table Assist with tear-down Assist with tallying |
| 0 |  | 157 |  | x | Staff Outreach table |
| 0 |  | 157 | x |  | Note results, but do NOT publish Total votes counted Number of provisional votes Votes per candidate |
| 0 |  | 157 |  |  | Empowerla tabulates the non-provisional ballots. If tallying the provisional ballots could not make a difference in the election results, they will not be tallied. If such is the case, the Final Official Certified Canvass of Votes shall be declared by empowerla. |
| +1 | 6 Jun | 158 |  |  | Or the day after votes are tallied, the IEA will post unofficial results on empowerla and send same to the neighborhood council |
| +1 | 6 Jun | 158 | x |  | Provide VNC president with contact info for all preliminary winning candidates |
| +3 | 8 Jun | 160 |  |  | Deadline for submission of documents validating provisional ballots |
| ? |  |  |  |  | Deadline for provisional ballot validation |
| ? |  |  |  |  | Deadline for empowerla to post the final official certified canvass of votes |
| +3 | 8 Jun | 160 |  |  | Deadline to request a recount |
| ? |  |  |  |  | The IEA will conduct requested recounts and immediately certify the recount results to the neighborhood council and empowerla. |
| +5 | 10 Jun | 162 |  |  | Deadline for filing a challenge regarding the conduct of the election. |
| ? |  |  |  |  | All challenges will be reviewed and resolved by the Neighborhood Council Grievance Panel. |
| ? |  |  |  |  | Deadline for resolving all challenges |
| ? |  |  |  |  | After all provisional votes are tallied (if necessary), and after all requested recounts have occurred, and after all challenges have been resolved empowerla (?) will certify the election results. |
| +30 to +60 | 5 Jul - 4 Aug | 187-217 |  |  | The Board is seated |
| +90 | 3 Sep | 247 |  |  | Deadline for neighborhood council to pick up election materials or empowerla will destroy them. |