2016 Venice Neighborhood Council Election Timeline

| Rel to Election Day | Date | Julian Date | Elec Comm | Outreach Comm | Activity |
| --- | --- | --- | --- | --- | --- |
| now |  |  | x | x | Joint Elections Committee/Outreach Committee meeting to determine roles and responsibilities of each |
| now |  |  |  | x | Create "Interested in Running for Board Seat" sign-up sheets. These sheets should be available at every VNC event until candidate filing begins. |
| now | for dist at 17 Nov VNC Board mtg |  |  | x | Create recruitment flyers, wording to be validated by elec comm |
| now |  |  | x |  | Create timeline merging empowerla events and VNC election activities, dates to be validated by outreach comm |
| now |  |  | x | x | Investigate newsletter creation and distribution costs |
| now |  |  |  | x | Investigate cost of outreach to apts/condos within boundaries - peninsula and southern portion of Oxford Triangle especially have Marina Del Rey addresses and may not know they are stakeholders in VNC. |
| now |  |  | x |  | Determine election events, approximate dates and approximate locations desired; Will there be a newsletter? Will newsletter photo be the same as that submitted to empowerla? Appoint newsletter liaison. |
| now |  |  | x |  | estimate costs to be covered by Elections Comm |
| now |  |  | x |  | Get budget for Elec Comm responsibilities -- done |
|  |  |  |  |  | If an election newsletter is wanted and feasible: - Select and secure publisher - Select and secure distributor - If photo other than what was submitted to emowerla will be allowed, add photo/stmt deadline to the election timeline (at least 3 weeks prior to the newsletter distribution date) |
|  |  |  |  | x | Plan the recruitment events - what will attract. - Event attendance should target by age (Senior citizens, middle age, young adults, youth 16 & up), consider ethnic groups, and be spread geographically within the boundaries of VNC - Themes - Publicity - Decoration handouts |
|  |  |  | x |  | Plan the programs for the recruitment events - Board members to attend - Photo-op - City officials |
|  |  |  |  | x | Secure locations for recruitment events |
|  |  |  |  | x | Secure refreshments for recruitment events |
|  |  |  | x |  | Secure additional resources for recruitment events - Photographer - Board Officers - Council Office - Mayor's Office - Testamonials |
|  |  |  | x |  | Secure location for Candidate Orientation |
|  |  |  | x |  | Secure refreshments for Candidate Orientation |
|  |  |  |  |  | Add VNC events and details to timeline on venicenc.org |
|  |  |  |  |  | Send list of VNC events to empowerla for their web site |
| -90 | 7 Mar | 67 |  |  | Candidate filing opens |
|  |  |  |  | x | Have candidate recruitment flyers available at every possible event, especially non-VNC events |
|  |  |  |  | x | Speak at meeting of other orgs, such as Chamber of Commerce, Recruit candidates by speaking at various organizations' meetings |
|  |  |  | x | x | Recruitment event 1 - mixer |
|  |  |  | x |  | Begin informative bulletins to prospective candidates. Continue bulletins to prospective and actual candidates until electon. They need lots of reminders about deadlines. |
|  |  |  |  |  | Plan Candidate Orientation program - Amount of time VNC responsibilities will require - Ethics training is required of all Board officers - Campaigning includes social media - Effective places to campaign - Effective ways to campaign |
|  |  |  |  |  | Develop and print Candidate Orientation handout materials. Campaign starter set - VOTE cards with candidate list - VOTE flyers - Campaign Guidelines |
|  |  |  | x | x | Recruitment event 2 |
|  |  |  |  |  | Preliminary plan for Board Orientation - Tutorials - By-laws - Whatever is normally covered - Council Office - City Atty Office |
|  |  |  | x | x | Recruitment event 3 |
|  |  |  |  |  | Immediately after recruitment event 3 |
| -60 | 6 Apr | 97 |  |  | Candidate filing closes |
|  |  |  |  |  | Candidate campaigning begins |
|  |  |  |  |  | Election Day volunteer recruitment begins |
| -57 | 9 Apr | 100 |  |  | empowerla deadline to submit candidate photos and statements for their web site |
| -57 | 9 Apr | 100 |  |  | deadline for submitting candidate's verifying documents |
| -57? |  |  |  |  | Empowerla releases the final verified list of candidates |
| -55 | 11 Apr | 102 | x |  | Candidate orientation |
| ?+3 |  |  |  |  | Deadline for challenging any candidate's eligibility |
|  |  |  |  | x | Voter awareness begins |
|  |  |  |  |  | Detailed plan for Board orientation |
| -45 | 21 Apr | 112 |  |  | Final day a candidate can withdraw and have name removed from the ballot |
| -45 | 21 Apr | 112 |  |  | City Clerk will release the final verified candidate list |
| -45 | 21 Apr | 112 |  |  | No later than this date, empowerla will give candidate contact information to his/her neighborhood council |
| -45 | 21 Apr | 112 |  |  | Voter drive begins |
| -45 | 21 Apr | 112 |  |  | Begin development of exit poll or survey |
| -45 | 21 Apr | 112 |  |  | Begin recruitment of voting process volunteers |
| -45 | 21 Apr | 112 |  |  | Begin recruitment of counting volunteers |
| -30 | 6 May | 127 |  |  | Deadline for empowerla to put election location on its web site. If changed, the change will be on the web site within 24 hours. |
|  |  |  |  |  | Complete arrangements for new Board's orientation - Requirements - Guest speakers - Tutorials - Absentees |
|  |  |  |  |  | Plan Forum(s) - Room layout - handouts - logistics for questions from audience - create samples to make sure there are adequate questions Question guidelines - Impartial - Not embarrassing - Confirm capability - Occupation - vision of Venice Neighborhood Council |
|  |  |  |  |  | Monitor newsletter preparation |
|  |  |  |  |  | Print all Forum Handouts |
| -21 | 15 May | 136 |  |  | Deadline for newsletter photos and statements |
|  |  |  |  |  | Print handouts, committee signup sheets, etc for outreach table that will be at poll exit |
| -10 | 26 May | 147 |  |  | Distribute newsletters |
| -3 | 2 Jun | 154 |  |  | Forum A |
| -2 | 3 Jun | 155 |  |  | Forum B |
| 0 | 5 Jun | 157 | x |  | Election day - Assist with election set-up - Assist with election - Assist at outreach table - Assist with tear-down - Assist with tallying |
| 0 |  | 157 |  | x | Staff Outreach table |
| 0 |  | 157 | x |  | - Note results, but do NOT publish - Total votes counted - Number of provisional votes - Votes per candidate |
| 0 |  | 157 |  |  | Empowerla tabulates the non-provisional ballots. If tallying the provisional ballots could not make a difference in the election results, they will not be tallied. If such is the case, the Final Official Certified Canvass of Votes shall be declared by empowerla. |
| +1 | 6 Jun | 158 |  |  | Or the day after votes are tallied, the IEA will post unofficial results on empowerla and send same to the neighborhood council |
| +1 | 6 Jun | 158 | x |  | Provide VNC president with contact info for all preliminary winning candidates |
| +3 | 8 Jun | 160 |  |  | Deadline for submission of documents validating provisional ballots |
| ? |  |  |  |  | Deadline for provisional ballot validation |
| ? |  |  |  |  | Deadline for empowerla to post the final official certified canvass of votes |
| +3 | 8 Jun | 160 |  |  | Deadline to request a recount |
| ? |  |  |  |  | The IEA will conduct requested recounts and immediately certify the recount results to the neighborhood council and empowerla. |
| +5 | 10 Jun | 162 |  |  | Deadline for filing a challenge regarding the conduct of the election. |
| ? |  |  |  |  | All challenges will be reviewed and resolved by the Neighborhood Council Grievance Panel. |
| ? |  |  |  |  | Deadline for resolving all challenges |
| ? |  |  |  |  | After all provisional votes are tallied (if necessary), and after all requested recounts have occurred, and after all challenges have been resolved empowerla (?) will certify the election results. |
| +30 to +60 | 5 Jul - 4 Aug | 187-217 |  |  | The Board is seated |
| +90 | 3 Sep | 247 |  |  | Deadline for neighborhood council to pick up election materials or empowerla will destroy them. |